## B9A status
item | status | qualification
classification | B9A COMPACT-WORKER FEASIBILITY PASS | Bounded B9A research only
gates | {"1": "PASS", "2": "PASS", "3": "PASS", "4": "PASS"} | Bounded B9A research only
scientificParity | PASS | Bounded B9A research only
failureRollback | PASS | Bounded B9A research only
responsivenessImprovement | YES | Bounded B9A research only
physicsThroughputImprovement | INCONCLUSIVE | Bounded B9A research only
startupImprovement | INCONCLUSIVE | Bounded B9A research only
memoryImprovement | INCONCLUSIVE | Bounded B9A research only
furtherIsolatedResearch | GO | Bounded B9A research only
operatorWorkstationIntegration | NO-GO | Bounded B9A research only
remainingPrimaryBottleneck | Solver/property evaluation | Bounded B9A research only
secondaryBottlenecks | ["Diagnostic copying", "Message transport", "Browser scheduling/rendering"] | Bounded B9A research only
B7Execution | DEFERRED | Bounded B9A research only
completeA2Qualification | False | Bounded B9A research only

## Inherited B8 blockers
issueId | severity | confidence | title | inputPair | currentA2Reachability | physicalAdmissibility | failureConsequence | unresolved | smallestCorrectiveMilestone | historicalSource | status
DU-148 | P2 | HIGH | Unresolved Gate B DU endpoint 148 | DmassUmass_INPUTS | CONDITIONAL: canonical recovery is required, but baseline accepted A2 uses table engine. Full-VLE CoolProp requires special isolated configuration. Saved native PH initialization construction matches A2 arithmetic; natural transient exact input reachability UNKNOWN. | UNRESOLVED; no original independent phase qualification | Can block conditional initialization or reject post-Newton recovery; persistent failure can halve to numerical stop. DU is outside PH signed Jacobian evaluation. No returned accepted phase for these exact replayed outcomes. | Four phases/reference separations; certified binary64 recovery; exact-inventory support. Dynamic trajectory reachability not established. | Keep parked until full-VLE exact-endpoint operation becomes a prioritized supported requirement; then bounded feasibility review under unchanged references. | browser_eos_b7/evidence/fixed-inputs.json#native-ledger-148; browser_eos_b5a_gate_b/evidence/four-case-reproduction-and-controls.json | OPEN
DU-162 | P2 | HIGH | Unresolved Gate B DU endpoint 162 | DmassUmass_INPUTS | CONDITIONAL: canonical recovery is required, but baseline accepted A2 uses table engine. Full-VLE CoolProp requires special isolated configuration. Saved native PH initialization construction matches A2 arithmetic; natural transient exact input reachability UNKNOWN. | UNRESOLVED; no original independent phase qualification | Can block conditional initialization or reject post-Newton recovery; persistent failure can halve to numerical stop. DU is outside PH signed Jacobian evaluation. No returned accepted phase for these exact replayed outcomes. | Four phases/reference separations; certified binary64 recovery; exact-inventory support. Dynamic trajectory reachability not established. | Keep parked until full-VLE exact-endpoint operation becomes a prioritized supported requirement; then bounded feasibility review under unchanged references. | browser_eos_b7/evidence/fixed-inputs.json#native-ledger-162; browser_eos_b5a_gate_b/evidence/four-case-reproduction-and-controls.json | OPEN
DU-164 | P2 | HIGH | Unresolved Gate B DU endpoint 164 | DmassUmass_INPUTS | CONDITIONAL: canonical recovery is required, but baseline accepted A2 uses table engine. Full-VLE CoolProp requires special isolated configuration. Saved native PH initialization construction matches A2 arithmetic; natural transient exact input reachability UNKNOWN. | UNRESOLVED; no original independent phase qualification | Can block conditional initialization or reject post-Newton recovery; persistent failure can halve to numerical stop. DU is outside PH signed Jacobian evaluation. No returned accepted phase for these exact replayed outcomes. | Four phases/reference separations; certified binary64 recovery; exact-inventory support. Dynamic trajectory reachability not established. | Keep parked until full-VLE exact-endpoint operation becomes a prioritized supported requirement; then bounded feasibility review under unchanged references. | browser_eos_b7/evidence/fixed-inputs.json#native-ledger-164; browser_eos_b5a_gate_b/evidence/four-case-reproduction-and-controls.json | OPEN
DU-165 | P2 | HIGH | Unresolved Gate B DU endpoint 165 | DmassUmass_INPUTS | CONDITIONAL: canonical recovery is required, but baseline accepted A2 uses table engine. Full-VLE CoolProp requires special isolated configuration. Saved native PH initialization construction matches A2 arithmetic; natural transient exact input reachability UNKNOWN. | UNRESOLVED; no original independent phase qualification | Can block conditional initialization or reject post-Newton recovery; persistent failure can halve to numerical stop. DU is outside PH signed Jacobian evaluation. No returned accepted phase for these exact replayed outcomes. | Four phases/reference separations; certified binary64 recovery; exact-inventory support. Dynamic trajectory reachability not established. | Keep parked until full-VLE exact-endpoint operation becomes a prioritized supported requirement; then bounded feasibility review under unchanged references. | browser_eos_b7/evidence/fixed-inputs.json#native-ledger-165; browser_eos_b5a_gate_b/evidence/four-case-reproduction-and-controls.json | OPEN
DP-01 | P3 | HIGH | 30298.937123458254-hg / default | DmassP_INPUTS | DIAGNOSTIC ONLY for current A2: complete dependency closure has no CoolProp DP call; no DP adapter method. Raw B7 loader exposes it experimentally. | REFUSED: invalid browser equilibrium quality; exact DP physical phase independently unqualified | No current A2 impact. Future raw DP consumer could use an inadmissible equilibrium state unless it refuses; phase enum alone cannot certify phase. | browser-endpoint-rounding-relative-to-native; independent exact-input phase qualification missing; broader DP interface NOT QUALIFIED | Reopen targeted DP admissibility work only with a demonstrated prioritized consumer. | browser_eos_b5a/evidence/shared-density.json#/rows/11; browser_eos_b7/evidence/quality-disposition.json | OPEN
DP-02 | P3 | HIGH | 350000.0-hg / default | DmassP_INPUTS | DIAGNOSTIC ONLY for current A2: complete dependency closure has no CoolProp DP call; no DP adapter method. Raw B7 loader exposes it experimentally. | REFUSED: invalid browser equilibrium quality; exact DP physical phase independently unqualified | No current A2 impact. Future raw DP consumer could use an inadmissible equilibrium state unless it refuses; phase enum alone cannot certify phase. | browser-endpoint-rounding-relative-to-native; independent exact-input phase qualification missing; broader DP interface NOT QUALIFIED | Reopen targeted DP admissibility work only with a demonstrated prioritized consumer. | browser_eos_b5a/evidence/shared-density.json#/rows/26; browser_eos_b7/evidence/quality-disposition.json | OPEN
DP-03 | P3 | HIGH | 350000.0-hf / default | DmassP_INPUTS | DIAGNOSTIC ONLY for current A2: complete dependency closure has no CoolProp DP call; no DP adapter method. Raw B7 loader exposes it experimentally. | REFUSED: invalid browser equilibrium quality; exact DP physical phase independently unqualified | No current A2 impact. Future raw DP consumer could use an inadmissible equilibrium state unless it refuses; phase enum alone cannot certify phase. | browser-endpoint-rounding-relative-to-native; independent exact-input phase qualification missing; broader DP interface NOT QUALIFIED | Reopen targeted DP admissibility work only with a demonstrated prioritized consumer. | browser_eos_b5a/evidence/shared-density.json#/rows/20; browser_eos_b7/evidence/quality-disposition.json | OPEN
DP-04 | P3 | HIGH | 30298.937123458254-hg / full VLE | DmassP_INPUTS | DIAGNOSTIC ONLY for current A2: complete dependency closure has no CoolProp DP call; no DP adapter method. Raw B7 loader exposes it experimentally. | REFUSED: invalid browser equilibrium quality; exact DP physical phase independently unqualified | No current A2 impact. Future raw DP consumer could use an inadmissible equilibrium state unless it refuses; phase enum alone cannot certify phase. | inherited-native-invalid-quality; independent exact-input phase qualification missing; broader DP interface NOT QUALIFIED | Reopen targeted DP admissibility work only with a demonstrated prioritized consumer. | browser_eos_b5a/evidence/shared-density.json#/rows/71; browser_eos_b7/evidence/quality-disposition.json | OPEN
DP-05 | P3 | HIGH | 350000.0-hg / full VLE | DmassP_INPUTS | DIAGNOSTIC ONLY for current A2: complete dependency closure has no CoolProp DP call; no DP adapter method. Raw B7 loader exposes it experimentally. | REFUSED: invalid browser equilibrium quality; exact DP physical phase independently unqualified | No current A2 impact. Future raw DP consumer could use an inadmissible equilibrium state unless it refuses; phase enum alone cannot certify phase. | inherited-native-invalid-quality; independent exact-input phase qualification missing; broader DP interface NOT QUALIFIED | Reopen targeted DP admissibility work only with a demonstrated prioritized consumer. | browser_eos_b5a/evidence/shared-density.json#/rows/86; browser_eos_b7/evidence/quality-disposition.json | OPEN
DP-06 | P3 | HIGH | 799999.9981754856-hg / full VLE | DmassP_INPUTS | DIAGNOSTIC ONLY for current A2: complete dependency closure has no CoolProp DP call; no DP adapter method. Raw B7 loader exposes it experimentally. | REFUSED: invalid browser equilibrium quality; exact DP physical phase independently unqualified | No current A2 impact. Future raw DP consumer could use an inadmissible equilibrium state unless it refuses; phase enum alone cannot certify phase. | inherited-native-invalid-quality; independent exact-input phase qualification missing; broader DP interface NOT QUALIFIED | Reopen targeted DP admissibility work only with a demonstrated prioritized consumer. | browser_eos_b5a/evidence/shared-density.json#/rows/101; browser_eos_b7/evidence/quality-disposition.json | OPEN
DP-07 | P3 | HIGH | 3500000.0-hg / full VLE | DmassP_INPUTS | DIAGNOSTIC ONLY for current A2: complete dependency closure has no CoolProp DP call; no DP adapter method. Raw B7 loader exposes it experimentally. | REFUSED: invalid browser equilibrium quality; exact DP physical phase independently unqualified | No current A2 impact. Future raw DP consumer could use an inadmissible equilibrium state unless it refuses; phase enum alone cannot certify phase. | inherited-native-invalid-quality; independent exact-input phase qualification missing; broader DP interface NOT QUALIFIED | Reopen targeted DP admissibility work only with a demonstrated prioritized consumer. | browser_eos_b5a/evidence/shared-density.json#/rows/116; browser_eos_b7/evidence/quality-disposition.json | OPEN
DP-08 | P3 | HIGH | 3500000.0-hf / full VLE | DmassP_INPUTS | DIAGNOSTIC ONLY for current A2: complete dependency closure has no CoolProp DP call; no DP adapter method. Raw B7 loader exposes it experimentally. | REFUSED: invalid browser equilibrium quality; exact DP physical phase independently unqualified | No current A2 impact. Future raw DP consumer could use an inadmissible equilibrium state unless it refuses; phase enum alone cannot certify phase. | inherited-native-invalid-quality; independent exact-input phase qualification missing; broader DP interface NOT QUALIFIED | Reopen targeted DP admissibility work only with a demonstrated prioritized consumer. | browser_eos_b5a/evidence/shared-density.json#/rows/110; browser_eos_b7/evidence/quality-disposition.json | OPEN
DP-09 | P3 | HIGH | 799999.9981754856-hf / full VLE | DmassP_INPUTS | DIAGNOSTIC ONLY for current A2: complete dependency closure has no CoolProp DP call; no DP adapter method. Raw B7 loader exposes it experimentally. | REFUSED: invalid browser equilibrium quality; exact DP physical phase independently unqualified | No current A2 impact. Future raw DP consumer could use an inadmissible equilibrium state unless it refuses; phase enum alone cannot certify phase. | inherited-native-invalid-quality; independent exact-input phase qualification missing; broader DP interface NOT QUALIFIED | Reopen targeted DP admissibility work only with a demonstrated prioritized consumer. | browser_eos_b5a/evidence/shared-density.json#/rows/95; browser_eos_b7/evidence/quality-disposition.json | OPEN
DP-10 | P3 | HIGH | 350000.0-hf / full VLE | DmassP_INPUTS | DIAGNOSTIC ONLY for current A2: complete dependency closure has no CoolProp DP call; no DP adapter method. Raw B7 loader exposes it experimentally. | REFUSED: invalid browser equilibrium quality; exact DP physical phase independently unqualified | No current A2 impact. Future raw DP consumer could use an inadmissible equilibrium state unless it refuses; phase enum alone cannot certify phase. | inherited-native-invalid-quality; independent exact-input phase qualification missing; broader DP interface NOT QUALIFIED | Reopen targeted DP admissibility work only with a demonstrated prioritized consumer. | browser_eos_b5a/evidence/shared-density.json#/rows/80; browser_eos_b7/evidence/quality-disposition.json | OPEN
DP-11 | P3 | HIGH | 30298.937123458254-hf / full VLE | DmassP_INPUTS | DIAGNOSTIC ONLY for current A2: complete dependency closure has no CoolProp DP call; no DP adapter method. Raw B7 loader exposes it experimentally. | REFUSED: invalid browser equilibrium quality; exact DP physical phase independently unqualified | No current A2 impact. Future raw DP consumer could use an inadmissible equilibrium state unless it refuses; phase enum alone cannot certify phase. | inherited-native-invalid-quality; independent exact-input phase qualification missing; broader DP interface NOT QUALIFIED | Reopen targeted DP admissibility work only with a demonstrated prioritized consumer. | browser_eos_b5a/evidence/shared-density.json#/rows/65; browser_eos_b7/evidence/quality-disposition.json | OPEN
BOUNDARY-chromium-ledger-64 | P2 | HIGH | chromium-ledger-64 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#chromium-ledger-64 | OPEN
BOUNDARY-chromium-ledger-65 | P2 | HIGH | chromium-ledger-65 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#chromium-ledger-65 | OPEN
BOUNDARY-chromium-ledger-67 | P2 | HIGH | chromium-ledger-67 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#chromium-ledger-67 | OPEN
BOUNDARY-chromium-ledger-68 | P2 | HIGH | chromium-ledger-68 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#chromium-ledger-68 | OPEN
BOUNDARY-chromium-ledger-70 | P2 | HIGH | chromium-ledger-70 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#chromium-ledger-70 | OPEN
BOUNDARY-chromium-ledger-75 | P2 | HIGH | chromium-ledger-75 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#chromium-ledger-75 | OPEN
BOUNDARY-chromium-ledger-79 | P2 | HIGH | chromium-ledger-79 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#chromium-ledger-79 | OPEN
BOUNDARY-webkit-ledger-64 | P2 | HIGH | webkit-ledger-64 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#webkit-ledger-64 | OPEN
BOUNDARY-webkit-ledger-65 | P2 | HIGH | webkit-ledger-65 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#webkit-ledger-65 | OPEN
BOUNDARY-webkit-ledger-67 | P2 | HIGH | webkit-ledger-67 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#webkit-ledger-67 | OPEN
BOUNDARY-webkit-ledger-68 | P2 | HIGH | webkit-ledger-68 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#webkit-ledger-68 | OPEN
BOUNDARY-webkit-ledger-70 | P2 | HIGH | webkit-ledger-70 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#webkit-ledger-70 | OPEN
BOUNDARY-webkit-ledger-75 | P2 | HIGH | webkit-ledger-75 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#webkit-ledger-75 | OPEN
BOUNDARY-webkit-ledger-79 | P2 | HIGH | webkit-ledger-79 strict 35-bar refusal | M/U/V → DmassUmass_INPUTS | CONDITIONAL: experimental browser adapter at 35 bar. Exact five-section initialization construction verified from saved PH; baseline table engine does not load this artifact; natural transient occurrence UNKNOWN. | NOT QUALIFIED; raw p/h/T closeness is not exact-inventory support | Can refuse startup and stage/record recovery; persistent numerical rejection/halving, possible absent record. Old untyped-domain logic could mislead physical stop; C1 removes that inference for typed property errors. | Rounded DU two-inside/five-outside versus exact rational MUV one-inside/six-outside per historical seven; missing global phase/topology and support certificate. | Bounded support/topology decision only when exact-boundary integration is immediately required; no guard exemption. | browser_eos_b7/evidence/support-attribution.json#webkit-ledger-79 | OPEN
INWARD-webkit-ledger-69 | P2 | HIGH | webkit-ledger-69 saved inward false acceptance hazard | M/U/V → DmassUmass_INPUTS | CONDITIONAL: demonstrable experimental adapter return at saved inventory; current baseline table does not consume it. Natural supported five-section trajectory not demonstrated. | UNQUALIFIED: mathematical outward inventory, returned binary64 pressure inward; full exact-inventory physical branch/topology not certified | Could bypass numerical support refusal and reach conditional thermal/hydraulic/wet diagnostics. No demonstrated baseline conservation contamination; returned properties do not overwrite stored M/U/V. Numerical closure cannot validate support or phase. | Certified pressure support, complete physical branch/topology, trajectory-exit proof. Do not claim P0 without supported current path evidence. | Separate numerical certification/topology review only for an immediately required boundary acceptance decision. | browser_eos_b7/evidence/c1-*-explicit-bar.json#hazards/webkit-ledger-69; browser_eos_b5b_c2_p1/BRANCH_AND_TOPOLOGY.md | OPEN
INWARD-webkit-ledger-76 | P2 | HIGH | webkit-ledger-76 saved inward false acceptance hazard | M/U/V → DmassUmass_INPUTS | CONDITIONAL: demonstrable experimental adapter return at saved inventory; current baseline table does not consume it. Natural supported five-section trajectory not demonstrated. | UNQUALIFIED: mathematical outward inventory, returned binary64 pressure inward; full exact-inventory physical branch/topology not certified | Could bypass numerical support refusal and reach conditional thermal/hydraulic/wet diagnostics. No demonstrated baseline conservation contamination; returned properties do not overwrite stored M/U/V. Numerical closure cannot validate support or phase. | Certified pressure support, complete physical branch/topology, trajectory-exit proof. Do not claim P0 without supported current path evidence. | Separate numerical certification/topology review only for an immediately required boundary acceptance decision. | browser_eos_b7/evidence/c1-*-explicit-bar.json#hazards/webkit-ledger-76; browser_eos_b5b_c2_p1/BRANCH_AND_TOPOLOGY.md | OPEN
TOPOLOGY | P2 | HIGH | Global equilibrium / convex-envelope obligation | DU / exact M/U/V support | CONDITIONAL: exact-boundary certification obligation; parked | UNPROVED full branch selection | Blocks unconditional exact-inventory boundary certificate; extra digits do not supply theorem | Supporting tangent, competing phases/domain completeness | Park; independent bounded theorem/domain review only for immediate acceptance need | browser_eos_b5b_c2_p1/BRANCH_AND_TOPOLOGY.md | OPEN
SHARED-PHASE-LABELS | P2 | HIGH | Inherited shared endpoint phase-label differences | PH / PS / PU and shared-caller endpoint controls | CONDITIONAL: PH is required for experimental A2; PS/PU lack current model edges; exact affected PH trajectory not demonstrated | Endpoint physical phase NOT newly qualified | Could affect wet/homogeneous branch interpretation if a merely numerical label is treated as physical qualification | Per-control physical certification before broader shared-caller qualification | Use existing resolved PH subset for isolated worker research; phase review only for prioritized affected PH consumer | browser_eos_b7/evidence/shared-native-audit.json | OPEN
RESPONSIVENESS | P2 | HIGH | Browser initialization / physics responsiveness | PH / DU / SAT workload | CONDITIONAL: B7 main-thread experimental browser use | Separate performance observation, not scientific failure | Visible operator interface can stall; patch causality not established | Whole five-section worker initialization/physics/IPC latency and error fidelity | Option C: isolated worker-first A2 performance research | browser_eos_b7/evidence/performance-summary.json; browser_eos_b7/PERFORMANCE_AND_MEMORY.md | OPEN
BROADER-QUALIFICATION | P2 | HIGH | Broader EOS-backed five-section and device qualification | Required PH / DU / SAT subset | PLANNED broader integration; no current production dependency | NOT QUALIFIED for broader backend/integration claims | Prevents claim of complete EOS-backed training simulator; device responsiveness and calibration also open | Transfer original acceptance matrix without erasing original passes; adaptive BE exploratory limitation separate | After worker study, focused qualification-gap inventory against exact existing archives; no duplicate campaign now | browser_eos_b7/ENGINEERING_REPORT.md; ROADMAP_A2.md | OPEN